## Risk Management
Risk Assessment | [9 empty] | 14 | Risk Management
Affected Team | ID | Root Cause | Description of the risk/issue + Impact | Effect |  |  |  | Total Effect | Probabilty | Severity (E*P) | Preventive Actions: | Contingent Action | Due date | Responsible | Action Detonator | State (open/close) | Progress notes
|  |  |  | Plan | Efforts | Cost | Quality |  |  |  | Avoid or Reduce | (what to do in case of)
Purchasing | 1 | Long-term project and the use of software with fluctuating prices in the market | Risk: Other competitors may offer a lower-cost solution | 1 | 1 | 5 | 4 | 5 | 2 | 10 | Negotiate with High Management and show benefits or the product on a long-term period against a license acquisition of an external software. | Begin negotiation with High Management and end-users’ Directors to show the benefits of using internal software against a license purchasing on a long-term basis. | 2024-05-31 | Team Leader | Product usage escalations & product complaints. | Open | -
Impact: We will not have the project budget under control, and may lose the project release
All | 2 | Team member suffers equipment loss due to theft or remote lockout | Problem: The source and assembly code of the database is inaccessible or lost. | 5 | 5 | 5 | 5 | 5 | 5 | 25 | Verify backups and/or drafts of the database among team members. | Verify that latest draft of the project is in the cloud and can be downloaded from the last status or update. | 2024-04-16 | DevOps/DB Analyst | Delay on producto release for due date. | Closed | Project review and bugs fixed, the database version was restored and project development could be resumed. 18-Apr-2024
|  |  | Impact: The project is stopped and the product is unusable, delaying the release of the product. | [7 empty] | Back up information both in physical format and in corporate cloud or cloud accounts to avoid data loss and rework. | File the corresponding complaint to the public ministry and follow up on the theft complaint.
All | 3 | Common sick illness | Problem: The entire team falls ill at the same time and/or key members may become ill at some critical moment in software development. | 3 | 3 | 3 | 3 | 3 | 3 | 9 | If a member is sick, return them home and, if possible, work remotely and connect virtually for important meetings if required so the member can recover properly. | Follow social distancing protocols in case of suffering from a respiratory illness (COVID, influenza, etc.) and take in consideration proper health measures. | - | All | The sick member notifies the project leader and preventive measures are immediately taken. | Open | Due to the global health situation, this case may be filed again, so it does not have a set validity or expiration date.
Impact: Failure to comply with the plan with the client
All | 4 | Software execution error | Problem: Project development does not connect properly between Database and Front end and causes errors. | 5 | 5 | 5 | 5 | 5 | 2 | 10 | Use simple programs to create tables and databases to connect them with software that is easy to manipulate and connect to avoid delays. | Request support from experts or other teams to review possible failures and/or missing connections and avoid delays in deliverables | 2024-05-25 | All | El software no corre o no se ejecuta como se programa/espera | Closed | A database expert was contacted and managed to connect the database to the software code and managed to fulfill the task of connecting and generating the requested files.
Impact: Delay in deliverables and rework causing economic losses

## Project Status
Project Status (as of End of May, 2024)
Jan 2024 | 2024-02-01 | 2024-03-01 | April 2024 | 2024-05-01 | June 2024 | Overall | Scope | People Management | Resources | Risks & Issues
Start | On track | On Track | Delayed | Delayed | Delayed | n | n | n | n | n
Overall Status: Program is deployed on test platform ready to be released on production, pending testing on end-users. |  |  |  | Route to Green: Will push testing to be delivered the final product before end of June 2024. |  |  | Leadership Decision: Will reconsider if program is viable to release on Production to High Management.
I/R | Description |  |  | Mitigation/Action |  |  | Severity |  | Owner | Target Date
R | Covid-19 or any disease that can get any team member |  |  | Have a backup plan & file documentation stored on a cloud or servers |  |  | Low |  | PM | -
I | Database / Program coding lost due to stolen equipment |  |  | Mitigate the consequences of the lost data and recover the process & project updates, save all updates |  |  | Medium |  | All | 2024-05-19
I | University strike |  |  | Align to the deadlines and process all work to deliver timely the product |  |  | Medium |  | All | 2024-05-11
Key Milestones |  | Priority | Baseline | Target | Status |  | Phase |  | Planned Activities (Milestones)
MVP |  | Medium | 2024-02-01 | 20-Apr-2024 | C |  | MVP |  | QA validation
Product Testing |  | Medium | Apr-2024 | 2024-05-15 | G |  | Product Testing |  | Testing Final Users
Product Releasing |  | High | 2024-05-01 | 2024-05-25 | A |  | Product Releasing |  | Product release & project closure
Project Management & Documentation |  | High | 2024-05-01 | 2024-05-31 | NS

## Project Charter
Project ID |  | 01-A |  |  | Expected Start Date
Project Name |  | FarmaFACT |  |  | Expected Completion
Project Manager |  | Victor Hugo Barrera |  |  | Estimated Cost
Project Sponsor |  | STC |  |  | Estimated Savings
Purpose
Develop and build a tool that can create and process within the same platform database & structure for capturing the product purchasing and digital billing to clients that could generate invoices based on CFDI 3.3 regulations and issuing payment receipts to employees.
Objective |  |  |  |  | Scope
Specific goals the project aims to achieve |  |  |  |  | Boundaries of the project, including what is in and out
Must have an intuitive & easy interface, so that implies to have a clean design and a clear browsing for end-user. |  |  |  |  | This program is not yet aligned with the 4.0 version of the CFDI tax setup, will require further development
Have multi-layer authentication methods and data encyption to secure the integrity and confidentiality of all the information |  |  |  |  | As a test program, it only includes limited values for products and end-user accounts
Implement real-time analytic tools to inspect & monitor all currency transactions (Tx) and relevant events, so all reports can trigger & show all relevant actions.
Deliverables |  |  |  |  | Stakeholders
Tangible or intangible products to be delivered |  |  |  |  | Key people with an interest in the project
A web-based application that lets the end-user log in as a different type (administrator/payroll employee/client/auditor) |  |  |  |  | External clients
Depending the user type the access setup differs and lets the user control the application depending the need. |  |  |  |  | Internal employees
Internal & external auditors
Roles & Responsibilities
| Name |  | Role |  | Responsibilities
| Aranza Abril Núñez Luna |  | Business Analyst (BA) |  | Responsible for making a quick analysis of the business needs and its solutions
| Diego Jair Crisantos Martinez |  | Testing Engineer (QA) |  | Responsible for making all testing cases once the application is created
| Issac Alexander Guerrero Prado |  | Developer (Dev) |  | Responsible for creating a solid and strong coding for all the process
| María Guadalupe Martínez Pavón |  | Database Analyst (DBA) |  | Responsible for building a solid and consistent database for the application purposes
| Víctor Hugo Barrera Arenas |  | Project Leader (PM) |  | Responsible to align the members of the team to deliver the product as per compliance and product requirements and be the head of the team for the STC
Tentative Schedule
| Milestone | Description |  |  | Start | Finish
| DB Testing | Have a functional database testing version of the platform |  |  | 2024-03-30 | 13-Apr-2024
| General Testing | Make minimal fixes & debug for general testing |  |  | 13-Apr-2024 | 27-Apr-2024
| Proving Evidences | Gather all testing evidences to fix & push deploy on production |  |  | 27-Apr-2024 | 11-May-2024
| App Deployment | Release the application on Production |  |  | 11-May-2024 | 2024-05-25
| Delivery & Project Closure | Changing controls & Project closure |  |  | 25-May-2024 | 1-Jun-2024
Risks & Mitigation
| Risk | Mitigation |  | Remarks
1 | Other competitors may offer a lower-cost solution | Negotiate with High Management and show benefits or the product on a long-term period against a license acquisition of an external software. |  | Will negotiate if needed the possibility to extend the delivery due date for the product releasing
2 | Team member suffers equipment loss due to theft or remote lockout | Verify backups and/or drafts of the database among team members. |  | Project review and bugs fixed, the database version was restored and project development could be resumed. 18-Apr-2024
Back up information both in physical format and in corporate cloud or cloud accounts to avoid data loss and rework.
3 | Common sick illness | If a member is sick, return them home and, if possible, work remotely and connect virtually for important meetings if required so the member can recover properly. |  | Due to the global health situation, this case may be filed again, so it does not have a set validity or expiration date.
4 | Software execution error | Use simple programs to create tables and databases to connect them with software that is easy to manipulate and connect to avoid delays. |  | A database expert was contacted and managed to connect the database to the software code and managed to fulfill the task of connecting and generating the requested files.
Approvals
| Name | Approval Date |  | Role
1 | Victor Hugo Barrera Arenas | 31-May-2024 |  | Project Manager
2
3
4
5

## RACI Matrix
Stage | Process | BA | QA | Dev | DBA | Leader
Analysis | Requirement List | R | A | C | C | I
| Database Analysis (DB) | I | A | C | C | I
| Design Analysis | C | R | I | I | A
Design | Database Modeling | I | A | C | C | I
| Graphic Interface Design | C | C | R | R | A
| Architecture Design | I | C | R | R | A
Development | Catalog Implementation | C | I | I | I | A
| Backend Development | I | A | R | R | I
| Graphic Interface Development | C | A | R | R | I
| Infrastructure Creation | C | A | R | R | I
| Flux Deployment Creation | I | A | R | I | I
| Containers Creation | I | R | A | I | I
Testing | DB Testing | R | A | C | I | I
| General Testing | A | R | I | C | A
| Proving Evidences | A | R | I | I | C
| GUI Units Testing | R | A | I | I | C
Product Release | App Deployment | R | C | I | I | A
Project management | Business Planning | 1 | 1 | 1 | 1 | R
| Risks Analysis | 1 | 1 | 1 | 1 | R
| Change Controls | 1 | 1 | 1 | 1 | R
| Delivery & Project Closure | C | R | I | C | A

## Timing Costs
Stage | Process | BA | QA | Dev | DBA | Leader
Analysis | Requirement List |  | 2 | 6 |  | 1.5
| Database Analysis (DB) | 3 |  | 1 |  | 0.5
| Design Analysis | 2 |  | 2 |  | 0.5
Subtotal |  | 5 | 2 | 9 | 0 | 2.5
Design | Database Modeling |  | 6 | 8 |  | 0.5
| Graphic Interface Design |  | 8 | 8 |  | 0.5
| Architecture Design |  |  | 2
Subtotal |  | 0 | 14 | 18 | 0 | 1
Development | Catalog Implementation |  |  | 6 |  | 0.5
| Backend Development |  | 60 | 60 |  | 0.5
| Graphic Interface Development |  | 40 |  | 90 | 0.5
| Infrastructure Creation |  | 12 | 6 | 15 | 0.5
| Flux Deployment Creation | 0.5 | 0.5 | 4 | 10 | 0.5
| Containers Creation |  |  | 8 |  | 0.5
Subtotal |  | 0.5 | 112.5 | 84 | 115 | 3
Testing | DB Testing |  |  |  |  | 0.5
| General Testing | 60 |  |  |  | 0.5
| Proving Evidences | 24 | 12 |  | 24 | 1
| GUI Units Testing |  |  |  | 44 | 0.5
Subtotal |  | 84 | 12 | 0 | 68 | 2.5
Product Release | App Deployment |  |  |  | 1.5 | 0.5
Subtotal |  | 0 | 0 | 0 | 1.5 | 0.5
Project management | Business Planning | 1 | 1 | 1 | 1 | 16
| Risks Analysis | 1 | 1 | 1 | 1 | 5
| Change Controls | 1 | 1 | 1 | 1 | 8
| Delivery & Project Closure |  |  |  | 0.5 | 1
Subtotal |  | 3 | 3 | 3 | 3.5 | 30
Total (h) |  | 92.5 | 143.5 | 114 | 186.5 | 39

## Operation Costs
Position | Monthly (MXN) | Yearly (MXN) | Daily (MXN) | Effective hours(h) | Project Cost (MXN)
QA | 30500 | 2287.5 | 190.63 | 92.5 | 17632.81
Business Analyst | 28500 | 2137.5 | 178.13 | 143.5 | 25560.94
Developer | 32500 | 2437.5 | 203.13 | 114 | 23156.25
DataBase Analyst | 30500 | 2287.5 | 190.63 | 186.5 | 35551.56
Leader | 42000 | 3150 | 262.5 | 39 | 10237.5
Total | 164000 | 12300 | 1025 | 575.5 | 112139.06